## Cover
QA Report
Sprint | : | Sprint 01
Project | : | DRIVER
Build | : | Build Virsion 01
Date | : | 27/9/23
Reporter | : | Takia Maliha

## Release Summary
Project Name Release Summary Report
Release Info |  | Browser & Device List
Release Name | 1 | # | Desktop web Browser | Version
Version Name | 1 | 1 | Crome
Start Date | 2023-09-25
End Date | 2023-09-26
QA Release Date | 2023-09-27
Release Status | N/A
Released By | Takia Maliha
Prepared By | Takia Maliha
Verified By | Abdul Qadir
Executed Test Type:
1 | Funcational
2 | UI

## Functionality Verification
Project Name Release Checklist
# | Module | TL Confirmation | Verified by QA | Status (by QA) | SE/TL Comment | QA Comment
1 | Login | Yes | Yes | NG | Yes | Bug #479790 Bug #479816 B_04 (Bug Report for DRIVER )
2 | Dashboard | Yes | Yes | NG | Yes | Bug #479859 Bug #479867 Bug #479892 Bug #479895 Bug #479898
3 | Account | Yes | Yes | OK | Yes
4 | Add a record | Yes | Yes | NG | Yes | B_11,B_12(Bug Report for DRIVER)
5 | Duplicate record | Yes | Yes | NG | Yes | #479900
6 | Record List page | Yes | Yes | OK | Yes
7 | Map | Yes | Yes | NG | Yes | Bug #479902 Bug #479901 B_09 ,B_05(Bug Report for DRIVER)
[N.B: We have checked all screens and found some major and minor issues, these are posted in Redmine and Bug report]

## Graphical Report
Test Case Execution Report
| Build Version No: | Build Virsion 01
| Total Test cases: | 121
| Test Environments (Browsers): | 1
| Total Executable test cases: | 117
| Test Cases Executed: | 117
| Passed: | 93
| Failed: | 11
| NE: | 0
| NA: | 7
WIP:
| Total Reported Bugs : | 11
| New | 11
| Rejected | 0
| Deferred | 0
| Duplicate | 0
| Assigned | 0
| Open | 0
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
| Closed | 0
| Blocker | 1
| Critical | 0
| Major | 6
| Minor | 4
| Trivial | 0
| Total: | 11
| Reported Bugs : (All Sprints) | 11
| New | 0
| Rejected | 0
| Deferred | 2
| Duplicate | 0
| Assigned | 0
| Open | 0
| Fixed | 0
| Retest | 0
| Verified | 0
| Re-open | 0
Closed
| Low | 2
| Medium | 1
| High | 6
| Urgent | 0
| Immediate | 0
| Total: | 9
Step-2: Sprint#3 Bug summary
Step-2: Sprint#3 Bugs Severity:
Total Bug summary
Total Bugs (Priority wise):

## Bug_list
Sprint1 Bug List
Bug Type | Quantity
UI: | 0
Functional: | 11
Total: | 11
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | 0
# | Bug ID | Bug Summary | Status | Priority | Severity
1 | Bug #479790: | Unclear Error Message for Credential-related Errors |  | Medium | Minior
2 | Bug #479816 | Error message Formatting Issue |  | Low | Minior
3 | Bug #479859 | Occurred date displays a default date range of the last three months instant of showing last two weeks date range from current date. |  | High | Major
4 | Bug #479867 | In occurred date range future date can be selected after selecting from date. |  | High | Major
5 | Bug #479885 | Motor Collision / মোটর সংঘর্ষ This line is not displaying properly in total economic loss and societal harm pop-up window |  | Low | Minor
6 | Bug #479892 | Language does not appropriately change in every function when click on English to Bangla |  | High | Major
7 | Bug #479895 | After clicking on the Black Spots by Severity from layer option in the Map, there were no black spots to be identified. |  | High | Major
8 | Bug #479898 | In the dashboard blue dots does not appear on the view all incident function from last two weeks incidents |  | High | Major
9 | Bug #479900 | When you click on the "Manage duplicate records" option, the page that should show potential duplicate records is not displaying any duplicate records as it should. |  | High | Blocker
10 | Bug #479901 | In the map interface, when both DMP Thana and DMP Traffic Division are selected simultaneously using the toggle button, a distinct boundary is not displayed as expected. |  | Low | Minior
11 | Bug #479902 | When choosing both the incident and heatmap from the map page, only the heatmap coverd in the map page |  | low | Minior
Functional Bugs:
Step-2: Sprint#3- Bug summary
UI Bugs:

## Bug_trend
Sprint | Test case | Bugs | Resolved | Trend
Sprint#1 | 121 | 11 | 0 | 0

## Defect density (hidden)
Sprint | Effort | Defect | Defect density | Defect density
Sprint#1 |  | 0 | #DIV/0! | #DIV/0!